## Stealthwatch
Customer Details
| Customer Name | XXX
| Project Name | Stealtwatch PDI
Deal ID
Project ID
LEVEL OF EFFORT |  |  | Leading Engineer | Engineer
|  | Task | Security NCE | Security NCE | Return Flights | Hotel Nights | Milestone | Total Eng Hours | Total Eng Days | MILESTONE DAYS | ESTIMATED DURATION
REQUIREMENTS & GOVERNANCE
|  | - Project Initiation & Kick-off | 0.5 | 0.5 |  |  | 1 | 8 | 1 | 1
|  | - Discovery & Workshops |  |  |  |  | 1 | 0 | 0
|  | - CRD creation/revision |  |  |  |  | 1 | 0 | 0
SOLUTION DESIGN PHASE
|  | - Workshops |  |  |  |  | 2 | 0 | 0 | 3
|  | - Draft Solution Design Document (SDD) |  |  |  |  | 2 | 0 | 0
|  | - Review & update | 1 | 1 |  |  | 2 | 16 | 2
|  | - Presentation to customer & final updates | 0.5 | 0.5 |  |  | 2 | 8 | 1
IMPLEMENTATION PLAN
|  | - Workshops |  |  |  |  | 3 | 0 | 0 | 3
|  | - Draft Implementation Plan |  |  |  |  | 3 | 0 | 0
|  | - Reviews & updates | 1 | 1 |  |  | 3 | 16 | 2
|  | - Presentation to customer & final updates | 0.5 | 0.5 |  |  | 3 | 8 | 1
TEST PLAN
|  | - Workshops |  |  |  |  | 4 | 0 | 0 | 2
|  | - Draft Test Plan (NRFU) |  |  |  |  | 4 | 0 | 0
|  | - Reviews & updates | 1 | 1 |  |  | 4 | 16 | 2
|  | - Presentation to customer & final updates |  |  |  |  | 4 | 0 | 0
- Automation Tool or Script Test
TEST EXECUTION (optional)
|  | - Workshops |  |  |  |  | 5 | 0 | 0 | 0
|  | - Build/configure lab |  |  |  |  | 5 | 0 | 0
|  | - Test Execution |  |  |  |  | 5 | 0 | 0
|  | - 3rd Party Integration Verification |  |  |  |  | 5 | 0 | 0
|  | - API Use Cases Verification |  |  |  |  | 5 | 0 | 0
|  | - Final Test Plan results |  |  |  |  | 5 | 0 | 0
IMPLEMENTATION
|  | - SW Installation (include all steatchwatch components) |  |  |  |  | 6 | 0 | 0 | 2
|  | - Basic Configuration |  |  |  |  | 6 | 0 | 0
|  | - ISE Integration and quarantine policy setup (optional) |  |  |  |  | 6 | 0 | 0
|  | - Old configuration migrate (optional) |  |  |  |  | 6 | 0 | 0
|  | - 3rd Party Integration (SIEM, like splunk) |  |  |  |  | 6 | 0 | 0
|  | - Post Configuration Check | 1 | 1 |  |  | 6 | 16 | 2
KNOWLEDGE TRANSFER & TRAINING
|  | - Knowledge transfer |  |  |  |  | 7 | 0 | 0 | 2
|  | - Training |  |  |  |  | 7 | 0 | 0
|  | - Site ready training | 1 | 1 |  |  | 7 | 16 | 2
|  | - Site permit, site compliance training |  |  |  |  | 7 | 0 | 0
DAY 2 SUPPORT SERVICES
|  | - Tunning |  |  |  |  | 8 | 0 | 0 | 0
|  | - Day 2 Support (T&M hours, if required) |  |  |  |  | 8 | 0 | 0
Buffer Reservation
|  | - Buffer Days | [5 empty] | 0 | 0 | 0
|  | Subtotal | 6.5 | 6.5 | 0 | 0 |  | 104 | 13 | 13 | 0
|  | Leading NCE hours: | 52
|  | Leading NCE days: | 6.5
|  | NCE hours: |  | 52
|  | NCE days: |  | 6.5
|  | Total CX hours: | 104
|  | Total CX days: | 13
FINANCIALS
| Milestone | Activity | CXC PM | T&E | Total Price
| 1 | SOLUTION REQUIREMENTS | #REF! | #REF! | #REF!
| 2 | SOLUTION DESIGN DOCUMENT | #REF! | #REF! | #REF!
| 3 | IMPLEMENTATION PLAN | #REF! | #REF! | #REF!
| 4 | TEST PLAN | #REF! | #REF! | #REF!
| 5 | IMPLEMENTATION SERVICES (DC & Reference Site only) | #REF! | #REF! | #REF!
| 6 | KNOWLEDGE TRANSFER | #REF! | #REF! | #REF!
| 7 | DAY 2 SUPPORT | #REF! | #REF! | #REF!
| 8 |  | #REF! | #REF! | #REF!
| 9 |  | #REF! | #REF! | #REF!
| 10 |  | #REF! | #REF! | #REF!
| 11 |  | #REF! | #REF! | #REF!
|  |  | #REF! | #REF! | #REF! | Cell should be green if cross-check is accurate
|  |  | Cost | Quote
|  | Costs per grade: | #REF!

## ISE
Customer Details
| Customer Name | XXX
| Project Name | ISE PDI
Deal ID
Project ID
LEVEL OF EFFORT |  |  | Leading Engineer | Engineer
|  | Task | Security NCE | Security NCE | Return Flights | Hotel Nights | Milestone | Total Eng Days | Total Eng Hours | MILESTONE DAYS | ESTIMATED DURATION
REQUIREMENTS & GOVERNANCE
|  | - Project Initiation & Kick-off | 0.5 | 0.5 |  |  | 1 | 1 | 8 | 1
|  | - Discovery & Workshops |  |  |  |  | 1 | 0 | 0
|  | - CRD creation/revision |  |  |  |  | 1 | 0 | 0
SOLUTION DESIGN PHASE
|  | - Workshops |  |  |  |  | 2 | 0 | 0 | 3
|  | - Draft Solution Design Document (SDD) |  |  |  |  | 2 | 0 | 0
|  | - Review & update | 1 | 1 |  |  | 2 | 2 | 16
|  | - Presentation to customer & final updates | 0.5 | 0.5 |  |  | 2 | 1 | 8
[7 empty] | 0 | 0 | 0
IMPLEMENTATION PLAN
|  | - Workshops |  |  |  |  | 3 | 0 | 0 | 3
|  | - Draft Implementation Plan |  |  |  |  | 3 | 0 | 0
|  | - Reviews & updates | 1 | 1 |  |  | 3 | 2 | 16
|  | - Presentation to customer & final updates | 0.5 | 0.5 |  |  | 3 | 1 | 8
TEST PLAN
|  | - Workshops |  |  |  |  | 4 | 0 | 0 | 2
|  | - Draft Test Plan (NRFU) |  |  |  |  | 4 | 0 | 0
|  | - Reviews & updates | 1 | 1 |  |  | 4 | 2 | 16
|  | - Presentation to customer & final updates |  |  |  |  | 4 | 0 | 0
|  | - Automation Tool or Script Test |  |  |  |  | 4
TEST EXECUTION (optional)
|  | - Workshops |  |  |  |  | 5 | 0 | 0 | 0
|  | - Build/configure lab |  |  |  |  | 5 | 0 | 0
|  | - Test Execution |  |  |  |  | 5 | 0 | 0
|  | - BYOD Test |  |  |  |  | 5
|  | - 3rd Party Integration Verification |  |  |  |  | 5
|  | - Old Configuration Migrate |  |  |  |  | 5
|  | - API Use Cases Verification |  |  |  |  | 5
|  | - Final Test Plan results |  |  |  |  | 5 | 0 | 0
IMPLEMENTATION
|  | - SW Installation | 1 | 1 |  |  | 6 | 2 | 16 | 4
|  | - Basic Configuration (AAA + Tacacs Policy + Simple Guest + DNAC Integration) |  |  |  |  | 6 | 0 | 0
|  | - Posture Implementation (optional) |  |  |  |  | 6 | 0 | 0
|  | - BYOD Implementation (optional) |  |  |  |  | 6 | 0 | 0
|  | - MDM Integration (optional) |  |  |  |  | 6 | 0 | 0
|  | - Complex Guest (optional) |  |  |  |  | 6 | 0 | 0
|  | - 3rd Party Integration (SAML, social media and etc) |  |  |  |  | 6
|  | - Post Configuration Check | 1 | 1 |  |  | 6 | 2 | 16
KNOWLEDGE TRANSFER & TRAINING
|  | - Knowledge transfer |  |  |  |  | 7 | 0 | 0 | 2
|  | - Training |  |  |  |  | 7 | 0 | 0
|  | - Site ready training | 1 | 1 |  |  | 7 | 2 | 16
|  | - Site permit, site compliance training |  |  |  |  | 7 | 0 | 0
DAY 2 SUPPORT SERVICES
|  | - Day 2 Support (T&M hours, if required) |  |  |  |  | 8 | 0 | 0 | 0
Buffer Reservation
|  | - Buffer Days | [5 empty] | 0 | 0 | 0
|  | Subtotal | 7.5 | 7.5 | 0 | 0 |  | 15 | 120 | 15 | 0
|  | Leading NCE hours: | 60
|  | Leading NCE days: | 7.5
|  | NCE hours: |  | 60
|  | NCE days: |  | 7.5
|  | Total CX hours: | 120
|  | Total CX days: | 15
FINANCIALS
| Milestone | Activity | CXC PM | T&E | Total Price
| 1 | SOLUTION REQUIREMENTS | #REF! | #REF! | #REF!
| 2 | SOLUTION DESIGN DOCUMENT | #REF! | #REF! | #REF!
| 3 | IMPLEMENTATION PLAN | #REF! | #REF! | #REF!
| 4 | TEST PLAN | #REF! | #REF! | #REF!
| 5 | IMPLEMENTATION SERVICES (DC & Reference Site only) | #REF! | #REF! | #REF!
| 6 | KNOWLEDGE TRANSFER | #REF! | #REF! | #REF!
| 7 | DAY 2 SUPPORT | #REF! | #REF! | #REF!
| 8 |  | #REF! | #REF! | #REF!
| 9 |  | #REF! | #REF! | #REF!
| 10 |  | #REF! | #REF! | #REF!
| 11 |  | #REF! | #REF! | #REF!
|  |  | #REF! | #REF! | #REF! | Cell should be green if cross-check is accurate
|  |  | Cost | Quote
|  | Costs per grade: | #REF!

## Firepower
Customer Details
| Customer Name | XXX
| Project Name | Firepower PDI
Deal ID
Project ID
LEVEL OF EFFORT |  |  | Leading Engineer | Engineer
|  | Task | Security NCE | Security NCE | Return Flights | Hotel Nights | Milestone | Total Eng Hours | Total Eng Days | MILESTONE DAYS | ESTIMATED DURATION
REQUIREMENTS & GOVERNANCE
|  | - Project Initiation & Kick-off | 0.5 | 0.5 |  |  | 1 | 8 | 1 | 1
|  | - Discovery & Workshops |  |  |  |  | 1 | 0 | 0
|  | - CRD creation/revision |  |  |  |  | 1 | 0 | 0
SOLUTION DESIGN PHASE
|  | - Workshops |  |  |  |  | 2 | 0 | 0 | 3
|  | - Draft Solution Design Document (SDD) |  |  |  |  | 2 | 0 | 0
|  | - Review & update | 1 | 1 |  |  | 2 | 16 | 2
|  | - Presentation to customer & final updates | 0.5 | 0.5 |  |  | 2 | 8 | 1
[7 empty] | 0 | 0 | 0
IMPLEMENTATION PLAN
|  | - Workshops |  |  |  |  | 3 | 0 | 0 | 3
|  | - Draft Implementation Plan |  |  |  |  | 3 | 0 | 0
|  | - Reviews & updates | 1 | 1 |  |  | 3 | 16 | 2
|  | - Presentation to customer & final updates | 0.5 | 0.5 |  |  | 3 | 8 | 1
TEST PLAN
|  | - Workshops |  |  |  |  | 4 | 0 | 0 | 2
|  | - Draft Test Plan (NRFU) |  |  |  |  | 4 | 0 | 0
|  | - Reviews & updates | 1 | 1 |  |  | 4 | 16 | 2
|  | - Presentation to customer & final updates |  |  |  |  | 4 | 0 | 0
- Automation Tool or Script Test
TEST EXECUTION (optional)
|  | - Workshops |  |  |  |  | 5 | 0 | 0 | 0
|  | - Build/configure lab |  |  |  |  | 5 | 0 | 0
|  | - Test Execution |  |  |  |  | 5 | 0 | 0
|  | - 3rd Party Integration Verification |  |  |  |  | 5 | 0 | 0
|  | - API Use Cases Verification |  |  |  |  | 5 | 0 | 0
|  | - Final Test Plan results |  |  |  |  | 5 | 0 | 0
IMPLEMENTATION
|  | - SW Installation (include FMC + FTD) | 1 | 1 |  |  | 6 | 16 | 2 | 8
|  | - Basic Configuration (ACP, IPS, HA) | 2 | 2 |  |  | 6 | 32 | 4
|  | - IPS Configuration |  |  |  |  | 6 | 0 | 0
|  | - Cisco Cloud Infra Integration (optional) |  |  |  |  | 6 | 0 | 0
|  | - Cisco On-prem AMP and/or TG integration (option) |  |  |  |  | 6 | 0 | 0
|  | - SSL decryption (optional) |  |  |  |  | 6 | 0 | 0
|  | - AAA and Realm Integration (optional) |  |  |  |  | 6 | 0 | 0
|  | - Trusetsec (optional) |  |  |  |  | 6 | 0 | 0
|  | - VPN (optional) |  |  |  |  | 6 | 0 | 0
|  | - Old configuration migrate (optional) |  |  |  |  | 6 | 0 | 0
|  | - 3rd Party Integration (optional) |  |  |  |  | 6 | 0 | 0
|  | - Post Configuration Check | 1 | 1 |  |  | 6 | 16 | 2
KNOWLEDGE TRANSFER & TRAINING
|  | - Knowledge transfer |  |  |  |  | 7 | 0 | 0 | 2
|  | - Training |  |  |  |  | 7 | 0 | 0
|  | - Site ready training | 1 | 1 |  |  | 7 | 16 | 2
|  | - Site permit, site compliance training |  |  |  |  | 7 | 0 | 0
DAY 2 SUPPORT SERVICES
|  | - Day 2 Support (T&M hours, if required) |  |  |  |  | 8 | 0 | 0 | 0
Buffer Reservation
|  | - Buffer Days | [5 empty] | 0 | 0 | 0
|  | Subtotal | 9.5 | 9.5 | 0 | 0 |  | 152 | 19 | 19 | 0
|  | Leading NCE hours: | 76
|  | Leading NCE days: | 9.5
|  | NCE hours: |  | 76
|  | NCE days: |  | 9.5
|  | Total CX hours: | 152
|  | Total CX days: | 19
FINANCIALS
| Milestone | Activity | CXC PM | T&E | Total Price
| 1 | SOLUTION REQUIREMENTS | #REF! | #REF! | #REF!
| 2 | SOLUTION DESIGN DOCUMENT | #REF! | #REF! | #REF!
| 3 | IMPLEMENTATION PLAN | #REF! | #REF! | #REF!
| 4 | TEST PLAN | #REF! | #REF! | #REF!
| 5 | IMPLEMENTATION SERVICES (DC & Reference Site only) | #REF! | #REF! | #REF!
| 6 | KNOWLEDGE TRANSFER | #REF! | #REF! | #REF!
| 7 | DAY 2 SUPPORT | #REF! | #REF! | #REF!
| 8 |  | #REF! | #REF! | #REF!
| 9 |  | #REF! | #REF! | #REF!
| 10 |  | #REF! | #REF! | #REF!
| 11 |  | #REF! | #REF! | #REF!
|  |  | #REF! | #REF! | #REF! | Cell should be green if cross-check is accurate
|  |  | Cost | Quote
|  | Costs per grade: | #REF!