## Stealthwatch
Customer Details
| Customer Name | XXX
| Project Name | Stealtwatch PDI
Deal ID
Project ID
LEVEL OF EFFORT |  |  | Leading Engineer | Engineer
|  | Task | Security NCE | Security NCE | Return Flights | Hotel Nights | Milestone | Total Eng Hours | Total Eng Days | MILESTONE DAYS | ESTIMATED DURATION
REQUIREMENTS & GOVERNANCE
|  | - Project Initiation & Kick-off |  |  |  |  | 1
|  | - Discovery & Workshops |  |  |  |  | 1
|  | - CRD creation/revision |  |  |  |  | 1
SOLUTION DESIGN PHASE
|  | - Workshops |  |  |  |  | 2
|  | - Draft Solution Design Document (SDD) |  |  |  |  | 2
|  | - Review & update |  |  |  |  | 2
|  | - Presentation to customer & final updates |  |  |  |  | 2
0
IMPLEMENTATION PLAN
|  | - Workshops |  |  |  |  | 3
|  | - Draft Implementation Plan |  |  |  |  | 3
|  | - Reviews & updates |  |  |  |  | 3
|  | - Presentation to customer & final updates |  |  |  |  | 3
TEST PLAN
|  | - Workshops |  |  |  |  | 4
|  | - Draft Test Plan (NRFU) |  |  |  |  | 4
|  | - Reviews & updates |  |  |  |  | 4
|  | - Presentation to customer & final updates |  |  |  |  | 4
- Automation Tool or Script Test
TEST EXECUTION (optional)
|  | - Workshops |  |  |  |  | 5
|  | - Build/configure lab |  |  |  |  | 5
|  | - Test Execution |  |  |  |  | 5
|  | - 3rd Party Integration Verification |  |  |  |  | 5
|  | - API Use Cases Verification |  |  |  |  | 5
|  | - Final Test Plan results |  |  |  |  | 5
IMPLEMENTATION
|  | - SW Installation (include all steatchwatch components) |  |  |  |  | 6
|  | - Basic Configuration |  |  |  |  | 6
|  | - ISE Integration and quarantine policy setup (optional) |  |  |  |  | 6
|  | - Old configuration migrate (optional) |  |  |  |  | 6
- 3rd Party Integration (SIEM, like splunk)
|  | - Post Configuration Check |  |  |  |  | 6
KNOWLEDGE TRANSFER & TRAINING
|  | - Knowledge transfer |  |  |  |  | 7
|  | - Training |  |  |  |  | 7
|  | - Site ready training |  |  |  |  | 7
|  | - Site permit, site compliance training |  |  |  |  | 7
DAY 2 SUPPORT SERVICES
|  | - Tunning |  |  |  |  | 8
- Day 2 Support (T&M hours, if required)
Subtotal
Leading NCE hours:
Leading NCE days:
NCE hours:
NCE days:
Total CX hours:
Total CX days:
FINANCIALS
| Milestone | Activity | CXC PM | T&E | Total Price
| 1 | SOLUTION REQUIREMENTS
| 2 | SOLUTION DESIGN DOCUMENT
| 3 | IMPLEMENTATION PLAN
| 4 | TEST PLAN
| 5 | IMPLEMENTATION SERVICES (DC & Reference Site only)
| 6 | KNOWLEDGE TRANSFER
| 7 | DAY 2 SUPPORT
8
9
10
11
Cell should be green if cross-check is accurate
|  |  | Cost | Quote
Costs per grade:

## ISE
Customer Details
| Customer Name | new test
| Project Name | ISE PDI
Deal ID
Project ID
LEVEL OF EFFORT |  |  | Leading Engineer | Engineer
|  | Task | Security NCE | Security NCE | Return Flights | Hotel Nights | Milestone | Total Eng Days | Total Eng Hours | MILESTONE DAYS | ESTIMATED DURATION
REQUIREMENTS & GOVERNANCE
|  | - Project Initiation & Kick-off | 0.5 | 0.5 |  |  | 1
|  | - Discovery & Workshops | 1 | 1 |  |  | 1
|  | - CRD creation/revision | 1 | 1 |  |  | 1
SOLUTION DESIGN PHASE
|  | - Workshops | 1 | 1 |  |  | 2
|  | - Draft Solution Design Document (SDD) | 4 | 4 |  |  | 2
|  | - Review & update | 1 | 1 |  |  | 2
|  | - Presentation to customer & final updates | 0.5 | 0.5 |  |  | 2
0
IMPLEMENTATION PLAN
|  | - Workshops |  |  |  |  | 3
|  | - Draft Implementation Plan | 4 | 4 |  |  | 3
|  | - Reviews & updates | 1 | 1 |  |  | 3
|  | - Presentation to customer & final updates | 0.5 | 0.5 |  |  | 3
TEST PLAN
|  | - Workshops |  |  |  |  | 4
|  | - Draft Test Plan (NRFU) | 4 | 4 |  |  | 4
|  | - Reviews & updates | 1 | 1 |  |  | 4
|  | - Presentation to customer & final updates |  |  |  |  | 4
|  | - Automation Tool or Script Test |  |  |  |  | 4
TEST EXECUTION (optional)
|  | - Workshops |  |  |  |  | 5
|  | - Build/configure lab | 0 | 0 |  |  | 5
|  | - Test Execution | 1 | 1 |  |  | 5
|  | - BYOD Test |  |  |  |  | 5
|  | - 3rd Party Integration Verification |  |  |  |  | 5
|  | - Old Configuration Migrate |  |  |  |  | 5
|  | - API Use Cases Verification |  |  |  |  | 5
|  | - Final Test Plan results |  |  |  |  | 5
IMPLEMENTATION
|  | - SW Installation | 1 | 1 |  |  | 6
|  | - Basic Configuration (AAA + Tacacs Policy + Simple Guest + DNAC Integration) | 3 | 3 |  |  | 6
|  | - Posture Implementation (optional) |  |  |  |  | 6
|  | - BYOD Implementation (optional) |  |  |  |  | 6
|  | - MDM Integration (optional) |  |  |  |  | 6
|  | - Complex Guest (optional) |  |  |  |  | 6
|  | - 3rd Party Integration (SAML, social media and etc) |  |  |  |  | 6
|  | - Post Configuration Check | 1 | 1 |  |  | 6
KNOWLEDGE TRANSFER & TRAINING
|  | - Knowledge transfer | 3 | 3 |  |  | 7
|  | - Training | 0.5 | 0.5 |  |  | 7
|  | - Site ready training | 1 | 1 |  |  | 7
|  | - Site permit, site compliance training |  |  |  |  | 7
DAY 2 SUPPORT SERVICES
|  | - Day 2 Support (T&M hours, if required) |  |  |  |  | 8
Subtotal
Leading NCE hours:
Leading NCE days:
NCE hours:
NCE days:
Total CX hours:
Total CX days:
FINANCIALS
| Milestone | Activity | CXC PM | T&E | Total Price
| 1 | SOLUTION REQUIREMENTS
| 2 | SOLUTION DESIGN DOCUMENT
| 3 | IMPLEMENTATION PLAN
| 4 | TEST PLAN
| 5 | IMPLEMENTATION SERVICES (DC & Reference Site only)
| 6 | KNOWLEDGE TRANSFER
| 7 | DAY 2 SUPPORT
8
9
10
11
Cell should be green if cross-check is accurate
|  |  | Cost | Quote
Costs per grade:

## Firepower
Customer Details
| Customer Name | XXX
| Project Name | Firepower PDI
Deal ID
Project ID
LEVEL OF EFFORT |  |  | Leading Engineer | Engineer
|  | Task | Security NCE | Security NCE | Return Flights | Hotel Nights | Milestone | Total Eng Hours | Total Eng Days | MILESTONE DAYS | ESTIMATED DURATION
REQUIREMENTS & GOVERNANCE
|  | - Project Initiation & Kick-off | 0.5 | 0.5 |  |  | 1
|  | - Discovery & Workshops |  |  |  |  | 1
|  | - CRD creation/revision |  |  |  |  | 1
SOLUTION DESIGN PHASE
|  | - Workshops |  |  |  |  | 2
|  | - Draft Solution Design Document (SDD) |  |  |  |  | 2
|  | - Review & update |  |  |  |  | 2
|  | - Presentation to customer & final updates |  |  |  |  | 2
0
IMPLEMENTATION PLAN
|  | - Workshops |  |  |  |  | 3
|  | - Draft Implementation Plan |  |  |  |  | 3
|  | - Reviews & updates |  |  |  |  | 3
|  | - Presentation to customer & final updates |  |  |  |  | 3
TEST PLAN
|  | - Workshops |  |  |  |  | 4
|  | - Draft Test Plan (NRFU) |  |  |  |  | 4
|  | - Reviews & updates |  |  |  |  | 4
|  | - Presentation to customer & final updates |  |  |  |  | 4
- Automation Tool or Script Test
TEST EXECUTION (optional)
|  | - Workshops |  |  |  |  | 5
|  | - Build/configure lab |  |  |  |  | 5
|  | - Test Execution |  |  |  |  | 5
|  | - 3rd Party Integration Verification |  |  |  |  | 5
|  | - API Use Cases Verification |  |  |  |  | 5
|  | - Final Test Plan results |  |  |  |  | 5
IMPLEMENTATION
|  | - SW Installation (include FMC + FTD) |  |  |  |  | 6
|  | - Basic Configuration (ACP, IPS, HA) |  |  |  |  | 6
|  | - Cisco Cloud Infra Integration (optional) |  |  |  |  | 6
|  | - SSL decryption (optional) |  |  |  |  | 6
|  | - ISE Integration (optional) |  |  |  |  | 6
|  | - Trusetsec (optional) |  |  |  |  | 6
|  | - VPN (optional) |  |  |  |  | 6
|  | - Old configuration migrate (optional) |  |  |  |  | 6
|  | - 3rd Party Integration (optional) |  |  |  |  | 6
|  | - Post Configuration Check |  |  |  |  | 6
KNOWLEDGE TRANSFER & TRAINING
|  | - Knowledge transfer |  |  |  |  | 7
|  | - Training |  |  |  |  | 7
|  | - Site ready training |  |  |  |  | 7
|  | - Site permit, site compliance training |  |  |  |  | 7
DAY 2 SUPPORT SERVICES
|  | - Day 2 Support (T&M hours, if required) |  |  |  |  | 8
Subtotal
Leading NCE hours:
Leading NCE days:
NCE hours:
NCE days:
Total CX hours:
Total CX days:
FINANCIALS
| Milestone | Activity | CXC PM | T&E | Total Price
| 1 | SOLUTION REQUIREMENTS
| 2 | SOLUTION DESIGN DOCUMENT
| 3 | IMPLEMENTATION PLAN
| 4 | TEST PLAN
| 5 | IMPLEMENTATION SERVICES (DC & Reference Site only)
| 6 | KNOWLEDGE TRANSFER
| 7 | DAY 2 SUPPORT
8
9
10
11
Cell should be green if cross-check is accurate
|  |  | Cost | Quote
Costs per grade: